## Design Validation Plan
Senior Capstone Design
Project: | AI for Agriculture (#54) |  | Primary Author: | Braydyn Proctor
Team: | CharAI |  | Date: | 2025-10-07
Design Validation Plan & Results (DVP&R) |  | This Doc Is Subject to change
Requirement | Test | Test Subject | Target Date | Result | Recommendation | Owner | Duration | V or P
The model must return predictions in under 10 seconds for datasets ≤10k rows | Measure model inference time on Azure ML | ML model hosted on Azure | 2026-02-01 | TBD | Optimize model or endpoint if runtime >10s | Braydyn | 5d | V
The API must correctly handle CSV uploads and return valid responses | Upload a sample CSV via frontend to verify backend POST endpoint | REST API (Django backend) | 2026-01-01 | TBD | Add input validation or error handling if API fails | Joe | 2d | V
The trained model should achieve ≥90% accuracy on validation data | Evaluate model using validation dataset and compute MAE/R² | TensorFlow model | 2026-03-01 | TBD | Retrain with additional data if accuracy <90% | Braydyn | 7d | V
The web interface must load fast and responsive on a standard connection | Perform Lighthouse and Chrome DevTools load time audit | React frontend hosted on Azure | 2026-04-01 | TBD | Optimize image and script sizes if load time exceeds 3s | Josh | 3d | V
Data preprocessing must produce standardized and complete outputs | Test mixed-unit datasets through preprocessing module | Data preprocessing script | 2026-02-01 | TBD | Adjust normalization pipeline or unit checks if inconsistencies found | Matt | 4d | V
The prescription map must be downloadable and GIS-compatible | Generate and download a GeoTIFF from the web UI | Download/export module | 2026-04-01 | TBD | Adjust file format or metadata if file fails to open in QGIS | Joe | 2d | P
The system must remain stable under multiple concurrent users | Perform a stress test simulating 50 concurrent connections | Azure deployment | 2026-05-01 | TBD | Scale Azure resources or optimize backend queries if system crashes | Josh | 3d | P
The system must anonymize user data according to privacy standards | Inspect anonymized dataset to ensure no identifying info remains | Data storage and anonymization module | 2026-05-01 | TBD | Revise anonymization script if identifiers remain | Matt | 2d | P
The system must produce accurate results with real-world farm data | Compare predictions against verified farmer yield data | Full-stack deployed prototype | 2026-05-01 | TBD | Calibrate model or retrain with real data if correlation <90% | Braydyn | 7d | P
The interface must be intuitive and user-friendly | Conduct 3 user tests and gather feedback | Web application UI | 2026-04-01 | TBD | Redesign confusing UI elements if user satisfaction <75% | Joe | 5d | P
Summary | Total | Completed | Pass Rates | Comments
Virtual Tests | 5 | 0 | -
Physical Testing | 5 | 0 | -
Overall | 10 | 0 | -