## Project Planner
CharAI Project Planner
| Select a period to highlight at right. A legend describing the charting follows. | [6 empty] | Period Highlight: | 5 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[9 empty] | 2025 | [16 empty] | 2026
[9 empty] | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | Part of May
Task # | ACTIVITY | PREREQ TASKS | ASSIGNED TO | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
0 | Project Presentations & Important Dates | None | All
0.1 | Snapshot Day #1 | Due: 10/21 | All | 7 | 1
0.2 | Concept Design Review | Due: 11/14 | All | 10 | 1
0.3 | Snapshot Day #2 | Due: 12/9 | All | 14 | 1
0.4 | Detailed Design Review | Due: 2/9 | All | 23 | 1
0.5 | Engineering Release | Due: 2/27 | All | 25 | 1
0.6 | Snapshot Day #3 | Due: 3/31 | All | 30 | 1
0.7 | EXPO Poster | Due: 4/22 | All | 33 | 1
0.8 | EXPO | Due: 4/30 | All | 34 | 1
1 | Defining Requirements | None |  | 1 | 4 | 1 | 4 | 100%
2 | Program Architecture & Development Plan | 1 |  | 5 | 3
2.1 | Draft system diagrams (dfd, class sequence, user flow, use cases, model data handling) | 1 |  | 5 | 1
2.2 | Draft architecture models (frontend, backend, model, APIs, db) | 1 |  | 6 | 1
2.3 | Set milestones & responsibilities for model and system development | 1 |  | 7 | 1
3 | Data Collection & Preprocessing | 2 |  | 8 | 4
3.1 | Assemble dataset (images, yield data, metadata) | 2 |  | 8 | 1
3.2 | Clean dataset (remove noise, labeling consistency) | 3.1 |  | 9 | 1
3.3 | Preprocess data | 3.2 |  | 10 | 1
3.4 | Documentation | 3.1 |  | 11 | 1
4 | Create Rapid Prototype (PoC) | 2.1-2.3, 3.1-3.4 |  | 12 | 4
4.1 | Build mock UI screens & wireframes | 2.1-2.3 |  | 12 | 1
4.2 | Implement barebones core functionality (key workflow, minimal code) | 4.1 |  | 13 | 1
4.3 | Create a simple baseline model | 3.1-3.4 |  | 14 | 1
4.4 | Test prototype internally | 4.2, 4.3 |  | 15 | 1
5 | Model Development | 3.1-3.4 |  | 12 | 7
5.1 | Design CNN architecture | 3.1-3.4 |  | 12 | 1
5.2 | Train baseline model | 5.1 |  | 13 | 2
5.3 | Evaluate performance | 5.2 |  | 15 | 1
5.4 | Iterate: tuning | 5.3 |  | 16 | 2
5.5 | Compare against metrics & select best-performing model | 5.4 |  | 18 | 1
6 | Detailed Design & Implementation | 4 |  | 16 | 6
6.1 | Frontend: implement main UI components | 4 |  | 16 | 3
6.2 | Backend: server logic & API endpoints | 4 |  | 16 | 3
6.3 | Database setup: store raw data, trained model version, results | 6.2 |  | 19 | 1
6.4 | Unit testing | 4 |  | 16 | 3
6.5 | System integration | 6.1-6.4 |  | 20 | 2
7 | Create a Functional MVP | 5, 6 |  | 22 | 3
7.1 | Deploy CNN model inside the full system | 5, 6 |  | 22 | 1
7.2 | Demonstrate yield predictions | 7.1 |  | 23 | 1
7.3 | Test MVP workflow with advisor / stakeholders | 7.2 |  | 24 | 1
8 | Testing & Validation | 7 |  | 25 | 2
8.1 | Systematic testing | 7 |  | 25 | 1
8.2 | Integration testing | 7 |  | 26 | 1
8.3 | Collect user feedback (maybe) | 7 |  | 25 | 2
9 | Polishing & Final Refinement | 7, 8 |  | 27 | 2
9.1 | Model inference speed | 8 |  | 27 | 1
9.2 | Improve UI/UX (error reporting, visualization of predictions) | 8 |  | 28 | 1
9.3 | Document everything | 7 |  | 27 | 2